## Phase Tracker
Phase | Name | Status | Key Deliverable | Key Metric | Result | Blockers | Files / Artifacts | Notes
1 | CfC/NCP Core | ✅ Done | CfC cell + NCP wiring in JAX | Unit tests | 8/8 passing | — | phase1_cfc_ncp.py | Cross-referenced all v1-v12 failures
2 | MLP Baseline | ✅ Done | MLP locomotion policy (Brax PPO) | Reward | 11.51 | — | phase2_mlp_baseline.py | Pivoted from custom PPO to MuJoCo Playground
3a | CfC Locomotion | ✅ Done | CfC policy beats MLP on Go1 | Reward (vs MLP) | 27.4 (2.38x) | — | phase3_cfc_brax_ppo.py | First CfC quadruped locomotion
3b | Recurrent CfC | ✅ Done | Hidden state carry through PPO | Reward | 26.6 | — | phase3b_complete.py | Normalizer corruption fixed, h evolves
4 | CBF Safety Layer | ✅ Done | 0th-order CBF with 10kHz proof | Unit tests / freq | 7/7 ✓ / 84kHz | — | phase4_soma_cbf_final.py | HOCBF failed (M too small), static CBF correct for PD joints
5 | Body-Level CBFs | 🔲 Todo | Roll/pitch limits, min height, CoM | Tip-over prevention | — | Needs Phase 4 env access | — | Compose on top of joint CBF
6 | Multi-Robot | 🔲 Todo | Train Go1+H1, test A1+Cassie | Zero-shot transfer accuracy | — | Needs H1 env setup | — | Validates 'any-robot URDF' claim
7 | MoE Integration | 🔲 Todo | 8 Expert CfC + Gate routing | Multi-task reward | — | Needs Phase 6 | — | v11 architecture: Backbone→Gate→Experts→Heads
8 | Deployment | 🔲 Todo | INT8 quant, AOT export, sub-500KB | Model size / CPU latency | — | Needs Phase 7 | — | C reimplementation of CBF for ARM
9 | H1 Torque CBF | 🔲 Todo | 2nd-order HOCBF with real M(q) | Velocity safety guarantee | — | Needs Phase 6 (H1 env) | — | mj_mulM for torque-controlled joints
10 | World Model | 🔲 Todo | CfC world model + imagination rollouts | Prediction accuracy | — | Needs Phase 3b policy | — | Original v12 Step 2/3 vision

## Capabilities
# | Category | Capability | Status | Phase Required | I/O Pattern | Robot(s) | Obs Dims | Act Dims | Validated On | Notes
1 | Locomotion | Forward walk | ✅ Done | 3a/3b | Velocity cmd → PD targets | Go1 | 48 | 12 | Colab H100, vx=1.0 | Reward 27.4, walking gait confirmed
2 | Locomotion | Velocity tracking (variable speed) | ✅ Done | 3a/3b | Velocity cmd → PD targets | Go1 | 48 | 12 | Colab H100 | Tested vx=0.5, 1.0, 1.5
3 | Locomotion | Omnidirectional walk | ✅ Done | 3a/3b | Velocity cmd → PD targets | Go1 | 48 | 12 | Colab H100, vy+yaw | Aggressive cmd: vx=1.5, vy=0.5, yaw=1.0
4 | Locomotion | Backward walk | 🟡 Partial | 3b (eval only) | Velocity cmd → PD targets | Go1 | 48 | 12 | — | Same policy, needs vx<0 eval
5 | Locomotion | Lateral walk (L/R) | 🟡 Partial | 3b (eval only) | Velocity cmd → PD targets | Go1 | 48 | 12 | — | Same policy, needs vy-only eval
6 | Locomotion | Turning in place | 🟡 Partial | 3b (eval only) | Velocity cmd → PD targets | Go1 | 48 | 12 | — | Same policy, needs yaw-only eval
7 | Locomotion | Heading tracking | 🟡 Partial | 3b (eval only) | Velocity cmd → PD targets | Go1 | 48 | 12 | — | Yaw command already supported
8 | Locomotion | Trotting | 🔲 Todo | 7 (MoE) | Gait cmd + vel → PD targets | Go1 | 48+ | 12 | — | Needs gait conditioning or MoE expert
9 | Locomotion | Bounding | 🔲 Todo | 7 (MoE) | Gait cmd + vel → PD targets | Go1 | 48+ | 12 | — | Walk These Ways style
10 | Locomotion | Galloping | 🔲 Todo | 7 (MoE) | Gait cmd + vel → PD targets | Go1 | 48+ | 12 | —
11 | Locomotion | Pacing | 🔲 Todo | 7 (MoE) | Gait cmd + vel → PD targets | Go1 | 48+ | 12 | —
12 | Locomotion | Pronking | 🔲 Todo | 7 (MoE) | Gait cmd + vel → PD targets | Go1 | 48+ | 12 | —
13 | Locomotion | Stair ascent | 🔲 Todo | 5+6 | Vel + height scan → PD targets | Go1/H1 | 48+187 | 12 | — | Rough terrain env, height scan obs
14 | Locomotion | Stair descent | 🔲 Todo | 5+6 | Vel + height scan → PD targets | Go1/H1 | 48+187 | 12 | —
15 | Locomotion | Slope ascent | 🔲 Todo | 5+6 | Vel + height scan → PD targets | Go1/H1 | 48+187 | 12 | —
16 | Locomotion | Slope descent | 🔲 Todo | 5+6 | Vel + height scan → PD targets | Go1/H1 | 48+187 | 12 | —
17 | Locomotion | Step over obstacle | 🔲 Todo | 5+6 | Vel + height scan → PD targets | Go1/H1 | 48+187 | 12 | — | Parkour-style, ETH approach
18 | Locomotion | Crawling / crouching | 🔲 Todo | 5 | Vel + height cmd → PD targets | Go1/H1 | 48+ | 12 | — | Body height as additional command
19 | Balance | Static balance (flat) | 🟡 Partial | 3b (implicit) | — (emergent) | Go1 | 48 | 12 | — | Trained via DR, not explicitly tested
20 | Balance | Dynamic balance (moving) | 🟡 Partial | 3b (implicit) | — (emergent) | Go1 | 48 | 12 | —
21 | Balance | Push recovery (lateral) | 🔲 Todo | 5 | — (emergent from DR) | Go1/H1 | 48 | 12 | — | Needs push perturbation eval
22 | Balance | Push recovery (frontal) | 🔲 Todo | 5 | — (emergent from DR) | Go1/H1 | 48 | 12 | —
23 | Balance | Push recovery (rear) | 🔲 Todo | 5 | — (emergent from DR) | Go1/H1 | 48 | 12 | —
24 | Balance | Fall prevention | 🔲 Todo | 5 | Body CBF (roll/pitch limit) | Go1/H1 | 48 | 12 | — | Phase 5 body-level CBF
25 | Balance | Fall recovery (prone) | 🔲 Todo | 6+7 | Orientation → standup torques | H1 | 48+ | 19+ | — | Humanoid standup task
26 | Balance | Fall recovery (supine) | 🔲 Todo | 6+7 | Orientation → standup torques | H1 | 48+ | 19+ | —
27 | Balance | Single-leg balance | 🔲 Todo | 5 | — (emergent) | Go1/H1 | 48 | 12 | —
28 | Balance | Balance on uneven terrain | 🔲 Todo | 5+6 | Proprioception → reactive | Go1/H1 | 48+187 | 12 | — | Rough terrain env
29 | Balance | Balance under payload | 🔲 Todo | 5+7 | — (CfC adapts via h) | Go1/H1 | 48 | 12 | — | RMA-style adaptation
30 | Balance | Balance during manipulation | 🔲 Todo | 6+7 | Whole-body coordination | H1 | 48+ | 19+ | —
31 | Posture | Stand from sit | 🔲 Todo | 6 | Posture cmd → joint trajectory | H1 | 48+ | 19+ | — | Humanoid only
32 | Posture | Sit from stand | 🔲 Todo | 6 | Posture cmd → joint trajectory | H1 | 48+ | 19+ | —
33 | Posture | Crouch | 🔲 Todo | 5 | Height cmd → PD targets | Go1/H1 | 48+ | 12 | — | Body height as command
34 | Posture | Kneel | 🔲 Todo | 6 | Posture cmd → joint trajectory | H1 | 48+ | 19+ | — | Humanoid only
35 | Posture | Lean (fwd/bwd/lateral) | 🔲 Todo | 5 | Torso orient cmd → PD targets | Go1/H1 | 48+ | 12 | —
36 | Posture | Torso orientation control | 🔲 Todo | 5 | Torso orient cmd → PD targets | Go1/H1 | 48+ | 12 | —
37 | Posture | Height adjustment | 🔲 Todo | 5 | Height cmd → PD targets | Go1/H1 | 48+ | 12 | —
38 | Posture | Weight shifting | 🔲 Todo | 5 | CoM cmd → PD targets | Go1/H1 | 48+ | 12 | —
39 | Manipulation | End-effector position tracking | 🔲 Todo | 6+9 | EE pos cmd → arm torques | H1 | 48+ | 19+ | — | Requires H1 arms
40 | Manipulation | End-effector orientation tracking | 🔲 Todo | 6+9 | EE orient cmd → arm torques | H1 | 48+ | 19+ | —
41 | Manipulation | 6DOF pose tracking | 🔲 Todo | 6+9 | EE pose cmd → arm torques | H1 | 48+ | 19+ | —
42 | Manipulation | Force-controlled contact | 🔲 Todo | 6+9 | Force cmd → impedance | H1 | 48+F | 19+K | — | Requires force sensing
43 | Manipulation | Compliant insertion | 🔲 Todo | 6+9 | Pose + compliance → torques | H1 | 48+F | 19+K | — | Peg-in-hole style
44 | Manipulation | Object handover | 🔲 Todo | 6+7 | Grasp cmd + release trigger | H1 | 48+F | 25+ | — | Requires hands
45 | Manipulation | Bimanual coordination | 🔲 Todo | 7 | Dual EE cmd → both arms | H1 | 48+ | 25+ | —
46 | Manipulation | Pinch grip | 🔲 Todo | 6+9 | Grip cmd → finger torques | H1+hands | 48+T | 25+ | — | Dexterous hand required
47 | Manipulation | Power grip | 🔲 Todo | 6+9 | Grip cmd → finger torques | H1+hands | 48+T | 25+ | —
48 | Manipulation | Precision placement | 🔲 Todo | 6+9 | Place cmd → arm+finger | H1+hands | 48+T | 25+ | —
49 | Manipulation | Finger-spread grasp | 🔲 Todo | 6+9 | Grip cmd → finger torques | H1+hands | 48+T | 25+ | —
50 | Manipulation | In-hand rotation | 🔲 Todo | 7+9 | Rotate cmd → finger torques | H1+hands | 48+T | 25+ | — | Most difficult manipulation
51 | Manipulation | Tool use | 🔲 Todo | 7+9 | Tool cmd → arm+grip | H1+hands | 48+T | 25+ | — | Sustained grip + arm motion
52 | Manipulation | Carrying while walking | 🔲 Todo | 6+7 | Vel + carry cmd → whole body | H1 | 48+ | 19+ | — | Loco-manipulation
53 | Manipulation | Finger dexterity | 🔲 Todo | 7+9 | Finger cmd → finger torques | H1+hands | 48+T | 12-16 | — | Shadow/Allegro/LEAP hand
54 | Compliance | Variable stiffness control | 🔲 Todo | 9 | Kp/Kd cmd → variable PD | H1 | 48 | 19+19 | — | Policy outputs (q_target, Kp, Kd)
55 | Compliance | Impedance mode transitions | 🔲 Todo | 9 | Mode cmd → Kp/Kd schedule | H1 | 48 | 19+19 | — | Stiff → soft transition
56 | Compliance | Compliant surface interaction | 🔲 Todo | 9 | Force + compliance → torques | H1 | 48+F | 19+19 | —
57 | Compliance | Force limiting | 🔲 Todo | 4+9 | CBF on contact forces | Go1/H1 | 48+F | 12 | — | CBF extension for force limits
58 | Compliance | Passive dynamics mode | 🔲 Todo | 9 | Zero Kp → gravity comp only | H1 | 48 | 19 | —
59 | Whole-Body | Walk + reach | 🔲 Todo | 6+7 | Vel + EE cmd → whole body | H1 | 48+ | 19+ | — | Unified loco-manipulation policy
60 | Whole-Body | Walk + carry | 🔲 Todo | 6+7 | Vel + carry → whole body | H1 | 48+ | 19+ | —
61 | Whole-Body | Stand + manipulate | 🔲 Todo | 6+7 | Stand + EE cmd → whole body | H1 | 48+ | 19+ | —
62 | Whole-Body | Crouch + reach | 🔲 Todo | 6+7 | Crouch + EE → whole body | H1 | 48+ | 19+ | —
63 | Whole-Body | Multi-limb coordination | 🔲 Todo | 7 | Multi-target → all limbs | H1 | 48+ | 19+ | —
64 | Robustness | Mass variation tolerance | 🟡 Partial | 3b (DR) | — (training condition) | Go1 | 48 | 12 | — | MuJoCo Playground default DR
65 | Robustness | Friction variation tolerance | 🟡 Partial | 3b (DR) | — (training condition) | Go1 | 48 | 12 | —
66 | Robustness | Motor degradation tolerance | 🔲 Todo | 7 (DR) | — (training condition) | Go1/H1 | 48 | 12 | — | Needs explicit motor strength DR
67 | Robustness | Sensor noise tolerance | 🟡 Partial | 3b (DR) | — (training condition) | Go1 | 48 | 12 | — | Default obs noise in playground
68 | Robustness | Latency tolerance | 🔲 Todo | 7 (DR) | — (training condition) | Go1/H1 | 48 | 12 | — | Random action delay injection
69 | Robustness | External disturbance rejection | 🔲 Todo | 5 | — (emergent from DR) | Go1/H1 | 48 | 12 | — | Push perturbation eval
70 | Robustness | Terrain variation adaptation | 🔲 Todo | 5+6 | — (CfC h adapts) | Go1/H1 | 48+187 | 12 | — | Rough terrain env
71 | Robustness | Actuator backlash compensation | 🔲 Todo | 7 (DR) | — (training condition) | Go1/H1 | 48 | 12 | —
72 | SOMA-Only | O(1) bounded inference | ✅ Done | 1+3a | CfC architecture | All | — | — | Phase 1 unit tests | CfC is constant-time by design
73 | SOMA-Only | WCET = BCET (no branching) | ✅ Done | 4 | CBF architecture | All | — | — | Phase 4 timing | No conditionals in compiled CBF
74 | SOMA-Only | CBF safety certificate | ✅ Done | 4 | 0th-order CBF proven | Go1 | — | — | 7/7 tests, 84kHz | q_target ∈ [q_min, q_max] ∀ inputs
75 | SOMA-Only | Frequency invariance | 🟡 Partial | 8 | CfC Δt parameter | All | — | — | — | CfC supports Δt, not tested across freqs
76 | SOMA-Only | Zero-shot URDF transfer | 🔲 Todo | 6 | Robot descriptor conditioning | A1, Cassie | — | — | — | Train Go1+H1, test A1+Cassie
77 | SOMA-Only | Cross-robot generalization | 🔲 Todo | 6+7 | MoE gate routing | All | — | — | —
78 | SOMA-Only | MoE expert interpretability | 🔲 Todo | 7 | Gate weight analysis | All | — | — | — | Which expert handles which task
79 | SOMA-Only | Sub-500KB / CPU-only | 🔲 Todo | 8 | INT8 + AOT export | All | — | — | — | Target: 244KB INT8, ARM Cortex

## Dashboard
SOMA v13 — Progress Dashboard
Overall Progress
Status | Count | % of Total
✅ Done | 6 | 7.595%
🟡 Partial | 10 | 12.66%
🔲 Todo | 63 | 79.75%
Total | 79 | 100%
Progress by Category
Category | Total | Done | Partial | Todo | % Complete
Locomotion | 18 | 3 | 4 | 11 | 27.78%
Balance | 12 | 0 | 2 | 10 | 8.333%
Posture | 8 | 0 | 0 | 8 | 0%
Manipulation | 15 | 0 | 0 | 15 | 0%
Compliance | 5 | 0 | 0 | 5 | 0%
Whole-Body | 5 | 0 | 0 | 5 | 0%
Robustness | 8 | 0 | 3 | 5 | 18.75%
SOMA-Only | 8 | 3 | 1 | 4 | 43.75%
Key Metrics Achieved
Metric | Value | Phase | Significance
CfC vs MLP reward | 2.38x (27.4 vs 11.5) | 3a | First CfC quadruped locomotion
CBF unit tests | 7/7 passing | 4 | Provable safety certificate
CBF throughput (compiled) | 84 kHz | 4 | 8.4x over 10kHz requirement
CBF batch throughput | 1.13B calls/sec | 4 | Training-scale safety
Reward loss (CBF on) | 0% forward, 1.1% aggressive | 4 | Zero performance degradation
CBF compute per env | 0.01 μs | 4 | 10,000x headroom for 10kHz
Real joint inertia M | 0.023 kg·m² | 4b | Discovered M_EFF was 26x wrong
Policy inference + CBF | < 1 μs total | 3+4 | Real-time on any hardware

## IO Patterns
Pattern # | Name | Command Input | Observation | Action Output | Capabilities Covered | Status | Robot(s)
P1 | Velocity Locomotion | vx, vy, yaw_rate (3D) | q_rel(12), qdot(12), gravity(3), gyro(3), prev_action(12), cmd(3), phase(2)=~48D | PD targets (12D) | Forward/back/lateral walk, turning, velocity tracking, heading, omnidirectional (8 capabilities) | ✅ Proven | Go1
P2 | Gait-Conditioned Locomotion | vx, vy, yaw + gait_params(8D) | P1 obs + gait_phase(2), gait_freq(1)=~51D | PD targets (12D) | Trot, bound, gallop, pace, pronk (5 capabilities) | 🔲 Todo | Go1
P3 | Terrain Locomotion | vx, vy, yaw (3D) | P1 obs + height_scan(187D)=~235D | PD targets (12D) | Stairs, slopes, obstacles, uneven terrain (6 capabilities) | 🔲 Todo | Go1/H1
P4 | Posture Control | body_height, torso_rpy (4D) | P1 obs + body_pose(6D)=~54D | PD targets (12-19D) | Crouch, lean, height adjust, weight shift, stand/sit (8 capabilities) | 🔲 Todo | Go1/H1
P5 | Balance / Recovery | — (reactive, no explicit cmd) | P1 obs + contact_forces(12D)=~60D | PD targets (12-19D) | Push recovery, fall prevention, single-leg, payload balance (10 capabilities) | 🟡 Implicit | Go1/H1
P6 | Arm Manipulation | EE_pose_target (6D) + grip_cmd (1D) | P1 obs + arm_q(7D), arm_qdot(7D), EE_pos(3D), EE_force(3D)=~68D | Arm torques or PD (7-19D) | EE tracking, force contact, insertion, handover (7 capabilities) | 🔲 Todo | H1
P7 | Dexterous Hand | grip_type(1D) + finger_targets(16D) | P6 obs + finger_q(16D), finger_qdot(16D), tactile(~48D)=~148D | Finger torques (16D) | Pinch, power grip, in-hand rotation, tool use (7 capabilities) | 🔲 Todo | H1+hands
P8 | Loco-Manipulation | vel(3D) + EE_target(6D) + grip(1D) | P1 + P6 obs combined=~80D | Whole-body (19-25D) | Walk+reach, walk+carry, stand+manipulate (5 capabilities) | 🔲 Todo | H1
P9 | Variable Impedance | q_target(ND) + Kp(ND) + Kd(ND) | P1 obs + contact_forces=~60D | q_target + Kp + Kd (3×N D) | Variable stiffness, compliance, force limiting (5 capabilities) | 🔲 Todo | H1
P10 | Robustness (DR) | — (training condition, not I/O) | Standard obs (varies by task) | Standard action (varies) | Mass/friction/motor/sensor/latency tolerance (8 capabilities) | 🟡 Partial | All
P11 | SOMA Properties | — (architectural, not I/O) | — | — | O(1), WCET, CBF, freq invariance, transfer, deploy (8 capabilities) | 🟡 Partial | All

## Unlock Gates
Gate | Name | Phases Required | Capabilities Unlocked | Count | Effort Estimate | Dependencies | Priority
G1 | Multi-Terrain Locomotion | 5 (Body CBFs) | Stairs, slopes, obstacles, crawl, terrain balance, push recovery, posture basics | ~15 | 2-3 days (training runs) | Rough terrain env setup | HIGH — demo impact
G2 | Multi-Robot + MoE | 6 + 7 | Cross-robot transfer, multi-gait, MoE interpretability, fall recovery | ~12 | 1-2 weeks | H1 env, MoE architecture | HIGH — investor story
G3 | Humanoid Manipulation | 6 + 9 | All 15 manipulation, 5 compliance, 5 whole-body, H1 torque CBF | ~30 | 3-4 weeks | H1 hands, force sensing, torque control | MEDIUM — biggest capability gap
G4 | Deployment Package | 8 | Freq invariance, sub-500KB, CPU-only, full DR validation | ~10 | 1 week | Stable policy from G1-G3 | HIGH — demo ready